**Roanoke-Chowan Community College - Presidential Search Timeline\***

**June 23, 2020** Board meets to discuss the search process and review and approve search timeline

**July 3, 2020** Progress Report #1 is posted along with electronic survey

**Mid August (TBD)** Special Board meeting for orientation and expectations of Board and Search Committee, and input on president profile.

**August 25, 2020** Board to approve president profile at regular meeting.

**Week of August 31, 2020** ACCT to commence local, state-wide and national recruitment. Presidential Profile posted on roanokechowan.edu and acctsearches.org websites. Targeted local, state-wide and national one-to-one recruitment and national advertising placed.

**October 13, 2020** **Target Date for Receipt of Applications (open until filled)**

**Oct. 14 – Oct. 20, 2020** Board Search Committee to review confidential applications independently through ACCT’s secure web portal.

**October 22, 2020** Board Search Committee meets to discuss and select confidential semifinalists (**Board** **Search Committee Meeting #2**)

**November 9 & 11, 2020** Board Search Committee meets to have confidential interviews semifinalists via video and recommend finalists (**Board Search Committee Meeting #3**).

**December 2, 2020** Continued review of semi-finalist candidates

**January 14, 2021** Continued review of semi-finalist candidates

**Late January, 2021** Final candidates interview with the full Board, participate in public forums, tour the College and meet with constituent groups. After the final interview, the Board deliberates. During deliberations, ACCT provides oral in-depth reference reports on final candidates.

**Week of February 1 , 2021** Board visits #1 candidate’s institution (optional but recommended).

**Week of February 8, 2021** ACCT facilitates final negotiations if desired by the Board. New President of Roanoke-Chowan Community College is announced.

**TBD** Start date for next President of Roanoke-Chowan Community College to be determined.